## Activity Tracker
Finosutra — Founder Activity Tracker
Last updated: 2026-06-24 ¦ Review weekly. Update Status as you go.
Total | Done | In Progress | Not Started | Blocked
16 | 1 | 0 | 15 | 0
# | Workstream | Task | Priority | Status | Next Action | Notes | Date Added
1 | Revenue & Sales | Get first real paying Pro subscriber (₹499/mo) | High | Not Started | DM 15-20 CAs/accountants from Krishna's own network directly with the tool link — warmest possible leads | Payment flow is fully built & tested — zero real conversions yet | 2026-06-25
2 | Marketing & Growth | Fix or pause the stalled Google Ads (Paid Search) campaign | High | Not Started | Do not resume broad Paid Search. If restarting: exact-match keywords only ("ind as 116 calculator", "ifrs 16 lease calculator"), Rs 500-1000/day cap, send clicks to homepage not indas116.html | Was 58% of all traffic but 0% conversion — money spent on clicks that bounced | 2026-06-25
3 | Marketing & Growth | Set up GA4 key events / conversion tracking | High | Not Started | Configure key events for purchase completions in GA4 | Currently can't measure true ad ROI without this | 2026-06-25
4 | Marketing & Growth | Add a lead-capture mechanism on /indas116.html | High | Not Started | Add an email-capture step ("email me this lease schedule") + a visible "Upgrade to Pro Rs 499/mo" banner on the result screen | Highest-traffic page (60% of sessions) but converts at 0% — highest-intent moment is being wasted | 2026-06-25
5 | Marketing & Growth | Post on Krishna's PERSONAL LinkedIn + DM outreach | High | Not Started | Post a short demo (screen recording) of the Ind AS 116 calculator from personal profile, not company page; DM the 15-20 CAs from the Revenue row above | Personal accounts outperform new company pages for early B2B trust; company page currently ~0 sessions/month | 2026-06-25
6 | Marketing & Growth | Answer Ind AS 116 / GST questions on CAclubindia & Quora | High | Not Started | Find 5-10 live threads asking how to calculate lease liability/ROU asset under Ind AS 116 or GST queries; answer genuinely, link the relevant calculator | High-intent, zero-cost — these are people already searching for exactly what the tool solves | 2026-06-25
7 | Marketing & Growth | Add testimonials / social proof to homepage | Medium | Not Started | Collect 2-3 quotes from the CAs reached via LinkedIn/DM outreach above once they've tried it | No trust signals on homepage yet — depends on outreach rows above | 2026-06-25
8 | GST & Compliance | Roll out GSTIN across the website | High | Done | — | Completed 2026-06-25 — all 19 customer-facing pages updated | 2026-06-25
9 | GST & Compliance | File first GSTR-1 / GSTR-3B (NIL return) | High | Not Started | Confirm filing frequency and due date; file via GST portal or a CA | Required even at Rs 0 revenue — missing it risks late fees | 2026-06-25
10 | GST & Compliance | Get Udyam (MSME) Registration Certificate | High | Not Started | Register free at udyamregistration.gov.in using Aadhaar + PAN — instant, self-declared, no documents to upload | Do this first — it's free, instant, and is one of the 2 govt-issued docs (with GST cert) banks need to open a current account | 2026-06-25
11 | GST & Compliance | Get PTEC (Professional Tax Enrollment Certificate) | High | Not Started | Apply via mahagst.gov.in within 30 days of GST registration; ~Rs 2,500/year flat fee, no return filing, just annual payment | Mandatory standalone Maharashtra compliance for every proprietor — separate legal obligation, not just a bank requirement | 2026-06-25
12 | GST & Compliance | Open a current account in "Finosutra" name | High | Not Started | Take GST certificate + Udyam certificate + PAN + Aadhaar to the bank (RBI requires 2 govt-issued business docs) | Blocked by Udyam registration above. Required before Razorpay Proprietorship KYC can be completed | 2026-06-25
13 | GST & Compliance | Migrate Razorpay account to Proprietorship type | High | Not Started | Start new Razorpay account KYC using PAN, GSTIN 27ACWPW1076G1ZX, and the new current account | Current account is "Individual" type — blocks GST linking. Blocked by the current account above. Cheapest time to switch is now, before real customers exist | 2026-06-25
14 | GST & Compliance | Build a manual GST invoice template | Medium | Not Started | Build a simple one-page invoice template to email for the first few sales | Faster than automating Razorpay invoicing at near-zero volume | 2026-06-25
15 | Product | Confirm gst-calculator.html is a working tool, not a stub | Low | Not Started | Krishna to confirm functionality | Page is getting real GA4 sessions but status is unverified | 2026-06-25
16 | Product | Scope GST Reconciliation tool (next product) | Low | Not Started | Define MVP scope once Pro flow has its first real customer | Next major product after the current calculators | 2026-06-25